## Backlog
Story | Backlog | Tasks | Volunteer | Tasks Details | Esitmated Efforts | Status
US001 | Create common Login System for Registration/Admission desk executive, Pharmacist and Diagnostic services executive | Task 1 | Adarsh | Create DBMS table “userstore” with login, password and timestamp column(s) | 0.5 | Closed | Open
|  | Task 2 | Harsh | Create User Login HTML Page Ref: Fig 1 Screens_HMS_Casestudy.pdf | 1 | Closed | In Progress
|  | Task 3 | Harsh | Create HTML Page to handle Invalid Login and handle Re login | 0.3 | Closed | Closed
|  | Task 4 | Adarsh | Create Servlet to Read login and password information from table and based on verification, options to allow user to continue to next pages or error message. | 2 | Closed
|  | Task 5 | Adarsh | Create Filter to validate HTTP Session | 1 | Closed
US002 | The functions of Registration/Admission desk | Task 1 |  | Create DBMS Patient table with fields : Patient SSN ID, Patient Name, Age, Date of admission, Type of bed(From drop down list with values General ward, semi sharing, single room),Address, City, State | 0.5 | Open
|  | Task 2 |  | Create DBMS Medicines Table with fields: Medicine ID, Medicine name, Quantity available, Rate of the medicine | 0.5 | Open
|  | Task 3 |  |  | 0.5 | Open
|  | Task 4 |  | Create DBMS Patient_Medicines Table with fields:Patient ID, ID of Medicine issued, Quantity issued | 0.5 | Open
|  | Task 5 |  | Create DBMS Patient_Diagnostics Table with fields: Patient ID, ID of Test conducted | 0.5 | Open
|  | Task 6 |  | Create HTML Page to Create Patient Ref: Fig 2 Screens_HMS_Casestudy.pdf. Refer to the constraints mentioned in SRS. Display error message on failure. | 2 | Open
|  | Task 7 |  | Create HTML Page to Update Patient Ref: Fig 2 Screens_HMS_Casestudy.pdf. Refer to the constraints mentioned in SRS. Display error message on failure. | 0.3 | Open
|  | Task 8 |  | Create HTML Page to Delete Patient Ref: Fig 4 Screens_HMS_Casestudy.pdf. | 0.3 | Open
|  | Task 9 |  | Create HTML Page to View All Patient Ref: Fig 5 Screens_HMS_Casestudy.pdf | 0.3 | Open
|  | Task 10 |  | Create servlet function Page to Create Patient Ref: Fig 2 Screens_HMS_Casestudy.pdf | 2 | Open
|  | Task 11 |  | Create servlet function to Update Patient Ref: Fig 3 Screens_HMS_Casestudy.pdf | 1 | Open
|  | Task 12 |  | Create servlet function Page to Delete Patient Ref: Fig 4 Screens_HMS_Casestudy.pdf | 0.5 | Open
|  | Task 13 |  | Create servlet function Page to View All Patient Ref: Fig 5 Screens_HMS_Casestudy.pdf | 0.5 | Open
|  | Task 14 |  | Create HTML Page to Search Patient Ref: Fig 6 Screens_HMS_Casestudy.pdf. Refer to the constraints mentioned in SRS. Display error message on failure. | 0.3 | Open
|  | Task 15 |  | Create servlet function Page to Search Patient | 0.5 | Open
|  | Task 16 |  | Create servlet function Page to display Patient Billing Details Ref: Fig 6 Screens_HMS_Casestudy.pdf | 0.3 | Open
|  | Task 17 |  | Create servlet function Page to Generate Patient Billing Details | 0.5 | Open
US003 | The functions of Pharmacists | Task 1 |  | Create HTML Page to Search Patient Ref: 5.2.1 in SRS. Display error message on failure. | 1 | Open
|  | Task 2 |  | Create HTML Issue Medicines Screen Ref: 5.2.2. in SRS. Display error message on failure. | 1 | Open
|  | Task 3 |  | Create servlet function Page to Search Patient | 1 | Open
|  | Task 4 |  | Create servlet function Page to issue medicines | 1 | Open
US004 | The functions of Diagnostics | Task 1 |  | Create HTML Page to Search Patient Ref: 5.3.1 in SRS. Display error message on failure. | 1 | Open
|  | Task 2 |  | Create HTML Diagnostics Screen Ref: 5.3.2. in SRS. Display error message on failure. | 1 | Open
|  | Task 3 |  | Create servlet function Page to Search Patient | 1 | Open
|  | Task 4 |  | Create servlet function Page to issue diagnostic tests | 1 | Open